# Scope of Work:

SAP Social Sabbatical for Global Engagement

TABLE OF CONTENTS

Ziyo Forum	2

Program Information	2

Partner Organization Information	2

Partner Organization Contacts	2

Partner Organization At-A-Glance	3

Organizational Description	4

Organizational History/Background	4

Key Products, Services, Programs	5

Markets, Customers, Clients, and/or Beneficiaries	5

Primary Partners, Stakeholders, & Influencers	6

ICT Systems & Platforms	7

Project Description	8

Background Context	8

Project Objective	8

Project Scope	9

Project Timing and Implementation	9

Knowledge and Information	10

Project Deliverables	11

Overall Impact	12

# Ziyo Forum

## Program Information

| Program Name | Team ID | Assigned Consultants |
| --- | --- | --- |
| SAP Social Sabbatical for Global Engagement | Uzbekistan 1 Tashkent | - Anja Fehlau (Germany) - Pankaj Bisht (India) - Stefanie Kruijen (Singapore) |
| Pyxera Global Program Manager | Project Start Date |  |
| Shilpa Ahluwalia | October 5, 2026 |  |
| Project Category/Type | Project End Date |  |
| Strategy or Roadmap | October 30, 2026 |  |
| Project Title |  |  |
| Growth Strategy and Roadmap (Ziyo app) |  |  |

## Partner Organization Information

| Organization Name |  |  |
| --- | --- | --- |
| Ziyo Forum |  |  |
| Website | Phone | Complete Address |
| https://ziyoforum.uz/ | +998 97 195-25-35 | Qushbegi 8, Tashkent, 100022, Uzbekistan |
| LinkedIn | Facebook | Twitter |
| (25) Ziyo Forum Foundation: Overview ¦ LinkedIn | Facebook | NA |

## Partner Organization Contacts

| Primary Project Contact | Title |
| --- | --- |
| Olimjon Xaitmuxamedov | Head of PR & Strategy department, Deputy director |
| Mobile Number | E-mail |
| +998 909901414 | alimkheyt@gmail.com |
| Secondary Project Contact | Title |
| Iskandar Samiev | Senior Specialist, PR and Strategy Department |
| Mobile Number | E-mail |
| +998 94-715-30-11 | iskandarsamiyev9@gmail.com |

## Partner Organization At-A-Glance

| Legal Structure - Sole proprietorship ☒ Non-profit - Foundation - Social enterprise - Partnership - Corporation - Limited liability company - Educational institution - Government - Other (please indicate) Business Model ☒ Service to Individuals/Households - Service to Small/Medium Enterprises/Entrepreneurs - Service to Nonprofits - Service to Government Operational Model - Distribution - Production/manufacturing of goods - Wholesale/retail ☒ Services - Financial services - Processing/packaging Organization Mission Statement: To improve the quality of education in Uzbekistan and strengthen the country’s youth talent pool by supporting science, innovation, and educational initiatives. Organization Vision Statement: To build a highly qualified, future-ready generation of young leaders, professionals, and innovators who contribute to Uzbekistan’s long-term social and economic development. | Project Sector Activities - Agriculture - Artisan/Handicraft - Business Support Services - Conflict Prevention & Recovery ☒ Culture - Disaster Resilience & Recovery - Economic Development ☒ Education - Employment Services - Energy - Environment/Sustainability - Financial Services - Food Security - Governance/Public Policy/Advocacy - Health - Housing Development - Information and Communications Technology - Infrastructure/Facilities Development - Manufacturing - Racial & Social Justice ☒ Research & Development - Social Services/Social Work - Supply Chain Services/Logistics - Transportation - Water - Other (please indicate) Financial Information: Prior year revenue/operating budget (USD): $1,450,000 Current year goal/operating budget (USD): $1,450,000 Number of Full Time Employees: 63 | Project Target Beneficiaries/Clients - Small- to Medium-sized Enterprises / Entrepreneurs - Government organizations - Non-governmental organizations - Social Enterprises/Social Entrepreneurs - Women and Girls - Pregnant People ☒ Children (0-17 years old) ☒ Young Adults (18-35 years old) - Older Adults (60+) - Underrepresented Ethnic or Racial Group - Indigenous ☒ People with Disabilities - People with Chronic Diseases/Illnesses - Disaster / Conflict Affected - Food Insecure People - Housing Insecure People - Economically Disadvantaged People - Unemployed People - Immigrants/Migrants - Refugees/Asylees/Displaced People - Veterans/Military - Incarcerated/Formerly Incarcerated People - LGBTQIA+ - Other (please indicate) Number of Beneficiaries/Clients Your Organization Currently Serves: In 2025, approximately 35,000 young people participated in the Foundation’s programs and initiatives. Geographic Areas Served (please specify) Uzbekistan, Tashkent |
| --- | --- | --- |

## Organizational Description

ZIYO Forum is a nonprofit organization established in 2019 and headquartered in Tashkent, Uzbekistan, working to advance science, education, culture, and youth development. Its mission is to improve access to quality education and strengthen Uzbekistan's youth talent pipeline by supporting educational, scientific, and innovation initiatives and creating opportunities for young people to develop their knowledge, skills, and potential.

ZIYO Forum serves a diverse group of beneficiaries, including school and university students, young professionals, aspiring researchers, women and girls, children, young adults, and people with disabilities. In 2025, the organization reached approximately 35,000 young people through its programs and initiatives and currently has approximately 63 full-time employees.

The organization delivers its mission through a range of educational platforms, media initiatives, research and development activities, and youth-focused programs. Its key initiatives include ZIYO APP, a digital platform connecting students and young people with educational and professional opportunities; ALLTEST, a free online learning and examination-preparation platform with more than 1,000 lessons; and AVLOD MEDIA, an educational media initiative focused on science, education, and youth engagement.

ZIYO APP is one of ZIYO Forum's strategic digital initiatives and is intended to provide young people with centralized access to scholarships, internships, grants, volunteer opportunities, events, educational programs, and other youth-focused resources.

ZIYO Forum's approximate annual operating budget is USD 1.45 million. Its primary sources of funding include endowment funding, grants, donations, and support from partner organizations. The organization aims to strengthen the quality and impact of its programs, scale successful initiatives, increase public awareness, and contribute to the development of Uzbekistan's national youth talent pipeline.

## Organizational History/Background

ZIYO Forum was established in 2019 in Tashkent, Uzbekistan as a nonprofit organization focused on advancing education, science, culture, and youth development. From its inception, the organization has sought to address gaps in access to quality educational resources and opportunities by developing platforms, programs, and initiatives that support young people's learning, skills development, and engagement with science and innovation.

Over time, ZIYO Forum has expanded its activities beyond traditional educational programming to include digital learning platforms, educational media, research and development initiatives, and youth-focused programs. This evolution has enabled the organization to reach a broader range of beneficiaries, including school and university students, young professionals, aspiring researchers, women and girls, children, young adults, and people with disabilities.

Among its key initiatives is ALLTEST, a free online learning and examination-preparation platform providing access to more than 1,000 lessons, and AVLOD MEDIA, an educational media initiative promoting science, education, and youth engagement. ZIYO Forum has also developed ZIYO APP as part of its broader effort to use digital technology to improve young people's access to educational and professional opportunities.

The organization has grown to approximately 63 full-time employees and reached an estimated 35,000 young people in 2025 across its programs and initiatives. As ZIYO Forum has expanded, its strategic focus has increasingly centered on improving the quality and impact of its programs, scaling successful initiatives, increasing public awareness, and strengthening Uzbekistan's national youth talent pipeline.

Today, ZIYO Forum continues to develop new platforms and partnerships that can expand access to education, skills development, and opportunities for young people across Uzbekistan, with ZIYO APP representing an important next step in the organization's digital and youth-development strategy.

## Key Products, Services, Programs

| Key Products/Services/ Programs | Description |
| --- | --- |
| ALLTEST | a free online learning and tutoring platform that enables school students to study and prepare for examinations remotely |
| ZIYO APP | a digital platform that expands access to educational resources and learning opportunities |
| AVLOD MEDIA | an educational media initiative that promotes science, education, and youth engagement through high-quality content |

## Markets, Customers, Clients, and/or Beneficiaries

| Market/Clients/ Beneficiaries | Description |
| --- | --- |
| School students | Young people seeking educational resources, extracurricular activities, scholarships, competitions, events, and opportunities to support their academic and personal development. |
| University students | Students seeking internships, scholarships, grants, volunteer opportunities, events, skills-development programs, and other academic and professional opportunities. |
| Young professional | Young adults seeking early-career opportunities, internships, entry-level employment, professional development, networking, and skills- building opportunities. |
| Aspiring researchers | Students, researchers, and early-career academics seeking research opportunities, grants, educational programs, conferences, and other opportunities to advance their academic and professional development. |
| Universities & Educational Institutions | Institutions seeking effective channels to communicate educational programs, events, scholarships, and other opportunities to students and young people. |
| Employers & Private-Sector Organizations | Companies seeking access to young talent through internships, entry-level opportunities, career programs, and youth-focused initiatives. |
| Government & Public Institutions | Government entities seeking to reach young people with educational, employment, development, civic engagement, and other youth-focused programs and opportunities. |

ZIYO Forum operates from Tashkent and its programs are designed to reach beneficiaries nationally across Uzbekistan. ZIYO APP's longer-term objective is to establish a nationwide digital platform that enables young people, regardless of their location, to discover and access relevant opportunities.

## Primary Partners, Stakeholders, & Influencers

| Partners/Stakeholders/ Influencers | Relationship to your organization | Relationship to the project |
| --- | --- | --- |
| Olimjon Xaitmuxamedov | Head of PR & Strategy department, Deputy director | Primary Contact for the SAP consultants for this program |
| Iskandar Samiev | Senior Specialist, PR and Strategy Department | Secondary Contact for the SAP consultants for this program |
| Bobur Farmanov | Director, ZIYO Forum | Executive sponsor and key decision-maker for the ZIYO APP strategy; provides strategic direction, validates recommendations, and supports alignment on priorities and implementation. |
| ZIYO Forum Leadership / Management | Provides strategic direction and oversight across the organization's programs and initiatives. | Key decision-makers for validating the strategic direction, priorities, resource requirements, and implementation roadmap for ZIYO APP. |
| Government Institutions | Government stakeholders involved in education, youth development, digitalization, employment, and related areas. | Important stakeholders for understanding the broader youth ecosystem, potential institutional partnerships, access to opportunities and information, and potential pathways for nationwide platform adoption. |
| Universities & Educational Institutions | Key ecosystem partners and potential providers of educational opportunities and information to students. | Critical to understanding student needs, developing user acquisition channels, sourcing opportunities, and building institutional partnerships for ZIYO APP. |
| Employers & Private-Sector Companies | Potential providers of internships, entry-level employment, training, and other opportunities for young people. | Important stakeholders for validating employer needs, strengthening the platform's value proposition, and developing partnership and opportunity-sourcing strategies |
| Nonprofit, Development & Youth Organizations | Providers of grants, volunteer opportunities, fellowships, events, training, and other youth-focused programs. | Potential content and ecosystem partners that can expand the range of opportunities available through ZIYO APP and strengthen the platform's reach and relevance. |
| ZIYO APP Users / Young People | Primary beneficiaries and users of the platform, including school students, university students, recent graduates, and young professionals. | Essential stakeholders for understanding user needs, pain points, adoption barriers, engagement drivers, and priorities for platform and user-experience improvements. |

## ICT Systems & Platforms

| System | Description |
| --- | --- |
| Videoconferencing (e.g. Zoom, Microsoft Teams, etc.) | Zoom |
| Document Storage & Collaboration (e.g. Google Suite, Microsoft Teams, etc.) | “Not Applicable” |
| Data management (e.g. Excel, Google Sheets, Oracle, etc.) | Excel and Google sheets |
| Customer Relationship Management (CRM) (e.g. SAP, Zoho, HubSpot, Salesforce, etc.) | “Not Applicable” |

# Project Description

## Background Context

ZIYO Forum has developed ZIYO APP as a digital platform intended to serve as a centralized entry point for students and young people seeking reliable information about educational, professional, and personal development opportunities. The platform brings together opportunities such as scholarships and grants, internships, volunteer programs, events, educational programs, and student-focused services that are otherwise often dispersed across university websites, social media channels, Telegram groups, employer platforms, government resources, and other sources. The platform addresses a significant challenge faced by young people in Uzbekistan: accessing relevant and trustworthy opportunities in an increasingly fragmented information environment. By bringing opportunities together in one digital ecosystem, ZIYO APP has the potential to make it easier for young people to discover opportunities aligned with their interests and development needs, while also creating a structured channel through which universities, employers, government institutions, nonprofit organizations, and other opportunity providers can reach young audiences.

ZIYO Forum has already launched the platform and established its core functionality. Initial user interest has demonstrated the potential value of a centralized youth opportunity platform. However, as ZIYO APP moves beyond its initial development stage, the organization faces several challenges in translating this potential into sustained user adoption, engagement, and nationwide scale. The platform needs greater clarity on which user segments and use cases should be prioritized, how it can differentiate itself from existing information and opportunity platforms, what will encourage users to return regularly, and which partnerships are most important to expanding the range and quality of opportunities available.

At the same time, ZIYO Forum needs to determine how the platform should evolve from a collection of opportunity listings into a trusted and user-centered digital ecosystem for youth. This requires a clearer understanding of user needs and journeys, priorities for product and user-experience improvements, approaches to content quality and trust, partner onboarding and management, and the organizational capabilities and governance required to operate the platform effectively at national scale.

ZIYO Forum therefore seeks support from the SAP consulting team to develop a growth and scaling strategy for ZIYO APP that is grounded in user needs, partnership opportunities, product priorities, and operational feasibility. The engagement will help the organization identify priority user segments, strengthen acquisition and retention approaches, develop a strategic partnership ecosystem, and establish priorities for future platform development and user experience. It will also provide a practical roadmap for scaling the platform across Uzbekistan and defining the organizational capabilities and performance indicators required to support that growth. Sustainability and potential revenue or funding models will be considered as part of the broader strategic assessment, but the primary focus of the engagement will be on increasing the platform's relevance, reach, user engagement, and social impact rather than developing a monetization strategy as a standalone objective.

This strategic direction will enable ZIYO Forum to make more informed decisions about future investment in the platform, partnerships, technology, communications, and organizational resources, while strengthening ZIYO APP's potential to become a widely accessible and trusted national resource for young people across Uzbekistan.

## Project Objective

The objective of this project is to develop a practical growth and scaling strategy for ZIYO APP that strengthens user acquisition, engagement, retention, partnerships, and the platform's overall value proposition for young people across Uzbekistan. The strategy will provide ZIYO Forum with a clear roadmap for scaling the platform nationally, prioritizing product and user-experience improvements,

strengthening its partnership ecosystem, and establishing the operational and sustainability foundations needed to deliver greater long-term impact for youth.

## Project Scope

ZIYO Forum seeks strategic consulting support to develop a practical growth and scaling strategy for ZIYO APP. The SAP consulting team will assess the platform's current positioning, functionality, user base, engagement, partnerships, and operating model to identify the key opportunities and barriers to achieving nationwide adoption and sustained user engagement.

The consultants will assess priority user segments and their needs, develop recommendations for user acquisition, onboarding, engagement, and retention, and identify opportunities to strengthen the platform's value proposition and differentiation from existing information and opportunity channels. The team will also assess and prioritize potential partnerships with universities, government institutions, employers, nonprofit organizations, and other ecosystem stakeholders, including recommendations for partner value propositions, onboarding, content contribution, and ongoing relationship management.

The engagement will include a strategic review of the platform's product and user experience to identify high-priority improvements, quick wins, and longer-term feature considerations based on user value, strategic importance, and implementation feasibility. The consultants will also provide recommendations on the operating model, governance, capabilities, and performance indicators required to manage and scale the platform effectively.

The project will culminate in a three-year growth and scaling roadmap outlining strategic priorities, phased actions, key partnerships, product and engagement priorities, ownership, dependencies, and measures of success. Sustainability and potential funding or revenue models may be considered as part of the broader assessment, with the primary focus remaining on building a widely adopted, trusted, and high-impact digital platform for young people across Uzbekistan.

## Project Timing and Implementation

ZIYO Forum has already launched ZIYO APP and established its core functionality, providing young people with access to educational opportunities, internships, grants, volunteer programs, events, and other youth-focused information. Initial user engagement has demonstrated demand for a centralized and reliable source of opportunities, validating the platform's underlying concept and social value.

As ZIYO APP moves from initial development toward broader adoption, the organization is reaching an important decision point. While the platform has significant potential, challenges remain in expanding its user base, increasing repeat engagement and retention, strengthening partnerships, and determining which product and user-experience improvements should be prioritized. Without a clear strategic direction, there is a risk that resources are spread across multiple product, marketing, technology, and partnership opportunities without sufficient focus on the areas that will generate the greatest user and social impact.

This is therefore an appropriate time for ZIYO Forum to step back and establish a clear three-year growth and scaling strategy before making significant further investments in platform development and expansion. The strategy will help align leadership and relevant teams around priority user segments, growth channels, partnerships, product priorities, operating requirements, and measures of success.

The four-week SAP Social Sabbatical engagement provides an opportunity to bring external expertise to this decision point, validate ZIYO Forum's current assumptions, incorporate stakeholder and user perspectives, and translate the organization's broader vision for ZIYO APP into a practical and prioritized roadmap for national growth.

Addressing these priorities now will enable ZIYO Forum to build on the platform's early momentum, strengthen its relevance and user engagement, and establish the foundations needed for ZIYO APP to become a trusted and widely accessible digital resource for young people across Uzbekistan.

## Knowledge and Information

The following information will be provided to the SAP consultants at the start of the project:

| Data Category | Information Required |
| --- | --- |
| User data | Registered users, monthly active users, daily active users, retention, geography, demographics, acquisition source, and conversion data. |
| Product data | Feature list, screenshots, product backlog, analytics, user feedback, technical architecture, and release history. |
| Growth data | Marketing campaigns, channels, budgets, performance, community activity, and referral mechanisms. |
| Content data | Number and categories of opportunities, source organizations, publishing frequency, quality- control process, and content performance. |
| Partnership data | Current partners, agreements, pipeline, partner contributions, and partnership performance. |
| Financial data | Annual platform costs, team costs, technology costs, funding sources, budget assumptions, and potential revenue concepts. |
| Impact data | Applications submitted, opportunities accessed, placements, scholarships, internships, volunteer participation, user outcomes, and available surveys. |
| Organization data | Team structure, roles, decision rights, governance, and key constraints. |

# Project Deliverables

Please note that the Scope of Work is a living document and as such, the deliverables may change after the pro bono consultants begin work. As such, the first project deliverable should be a Revised Scope of Work sent to the Project Manager by the end of Week 1.

| Deliverable | Description of Activities to Obtain Deliverables | Anticipated Impact |
| --- | --- | --- |
| 1. Revised Scope of Work | Discovery process to understand how much can be achieved by the SAP team, considering the needs of the partner organization, the skill sets of the SAP team, and the project timeline. | Expectations-setting and alignment on final deliverables between the SAP team and the partner organization. |
| 2. Current-State & User Opportunity Assessment | Assess ZIYO APP's current functionality, user base, engagement data, positioning, operating model, partnerships, and available capabilities. Identify priority user segments, user needs, pain points, high-value use cases, and key barriers to adoption and retention. Benchmark relevant local and international platforms to identify opportunities for differentiation. | Provides ZIYO Forum with a clear understanding of its current position, priority audiences, user needs, and the most important opportunities and gaps to address before scaling the platform nationally. |
| 3. Growth, User Engagement & Partnership Strategy | Develop recommendations for user acquisition, onboarding, engagement, retention, and reactivation across priority user segments. Define a partnership ecosystem covering universities, government institutions, employers, NGOs, media, and other relevant stakeholders, including partner value propositions, acquisition priorities, onboarding, and relationship management approaches. | Enables ZIYO APP to grow its user base, increase sustained engagement, strengthen its ecosystem of opportunity providers, and create greater value for young people and institutional partners. |
| 4. Product, User Experience & Operating Model Recommendations | Review the platform from a strategic and user-experience perspective and identify priority product improvements, quick wins, and longer-term feature considerations. Recommend improvements to content | Provides ZIYO Forum with clear priorities for future product development and the organizational capabilities needed to operate a trusted, user-centered platform at national scale. |

|  | quality, discovery, personalization, accessibility, user support, and other relevant functions. Define the operating capabilities, governance, roles, and processes required to support platform growth and effective partnership management. |  |
| --- | --- | --- |
| 5. Three-Year Growth & Scaling Roadmap | Consolidate findings into a phased three-year roadmap covering strategic priorities, user growth and engagement, partnerships, product development, operating requirements, resource considerations, ownership, dependencies, KPIs, and immediate 90-day actions. Where appropriate, include high-level recommendations on funding and sustainability options that support the platform's long-term viability without compromising its social mission. | Gives ZIYO Forum a practical and prioritized roadmap for scaling ZIYO APP nationally, aligning future investments and resources, measuring progress, and increasing the platform's long-term reach and impact among young people across Uzbekistan. |
| 6. (Optional – If Time Permits) Sustainability & Funding Recommendations | Assess potential funding and sustainability approaches for ZIYO APP, including institutional partnerships, sponsorships, grants, and other mission-aligned models. Consider potential revenue-generating approaches only where relevant and assess risks such as mission drift, accessibility, and user trust. | Provides ZIYO Forum with additional options for maintaining the platform's long-term sustainability while protecting its accessibility and youth-focused social mission. |

## Overall Impact

The expected impact of this engagement is to provide ZIYO Forum with a clear and evidence-based strategy for strengthening and scaling ZIYO APP as a trusted digital platform for young people across Uzbekistan. By clarifying priority users, strengthening the platform's value proposition, improving user acquisition and engagement, developing a stronger partnership ecosystem, and prioritizing future product and operational investments, the project will help ZIYO Forum make more informed decisions about how to grow the platform and maximize its social impact.

For ZIYO Forum, the engagement will provide greater strategic clarity and focus, enabling leadership to prioritize investments, partnerships, product improvements, and organizational resources based on user needs, available data, and implementation feasibility. A clear growth and scaling roadmap will also help

align the teams and stakeholders responsible for the platform around a common direction and measurable priorities.

For young people across Uzbekistan, a stronger and more accessible ZIYO APP has the potential to improve awareness of and access to educational, professional, and personal development opportunities, including internships, scholarships, grants, volunteer programs, events, and other youth-focused initiatives. Increased engagement with the platform can help strengthen connections between young people and universities, employers, government institutions, nonprofit organizations, and other opportunity providers.

Over the longer term, successful implementation of the strategy can contribute to a more connected national ecosystem for youth development, making relevant opportunities easier to discover and helping young people participate more actively in education, employment, entrepreneurship, volunteering, and other forms of civic and professional engagement.

Success for this project will be defined by ZIYO Forum receiving a practical, prioritized, and evidence-based strategy that can guide real management and investment decisions. The strategy should provide clear recommendations on priority users, growth and engagement approaches, partnerships, product and user-experience priorities, operating requirements, and implementation sequencing, while remaining realistic about ZIYO Forum's available resources and capabilities.

### Indicative success measures include:

### Short-term (upon project completion):

- A clear and prioritized growth and scaling strategy endorsed by ZIYO Forum leadership.

- Defined priority user segments, key use cases, and user engagement opportunities.

- A prioritized partnership ecosystem and outreach approach.

- Clear product, user-experience, and operating priorities.

- A three-year implementation roadmap with owners, dependencies, resources, milestones, and KPIs.

### Medium-term (6–12 months):

- Implementation of priority growth and user engagement initiatives.

- Increased user acquisition and repeat engagement.

- Growth in the number and quality of university, employer, government, nonprofit, and other ecosystem partnerships.

- Improved availability, quality, and discoverability of opportunities on the platform.

### Long-term (1–3 years):

- Sustained growth and engagement among young people across Uzbekistan.

- Increased participation in internships, scholarships, grants, volunteer programs, events, and other opportunities facilitated through the platform.

- Stronger connections between youth and opportunity providers.

- ZIYO APP established as a trusted and widely accessible national resource supporting youth education, employment, and development.