STATEMENT OF WORK  ·  FINAL

SAP Social Sabbatical × Ziyo Forum

4-Week Engagement Plan  ·  6 – 31 October 2026  ·  Tashkent, Uzbekistan

Interviews complete  ·  Week 1 finalized  ·  Based on 6 stakeholder discovery sessions

Ziyo Forum's 6 Expectations from SAP — The Organizing Principle

Every deliverable, workshop, and recommendation in this engagement maps directly to one of Ziyo Forum's six stated expectations. This is not a generic consultancy output — it is a response to what Ziyo Forum asked for.

| # | Pillar | In Plain Terms | Delivery Week |
| --- | --- | --- | --- |
| 1 | Growth Strategy | Identify the most effective ways to attract, activate and retain young users | Week 2 |
| 2 | Product & UX | Identify the most important product and user-experience improvements | Week 2 |
| 3 | Partner Strategy | Develop a scalable approach to acquiring and managing universities, companies, NGOs, cultural institutions and other partners | Week 3 |
| 4 | Analytics & KPIs | Define the metrics and dashboards needed to manage growth based on data | Week 3 |
| 5 | Operating Model | Make internal processes more structured and scalable | Week 3 |
| 6 | 3-Year Roadmap | Translate all findings into clear priorities, responsibilities and milestones | Week 4 |

4-Week Engagement Overview

|  | Week 1 6–10 Oct | Week 2 13–17 Oct | Week 3 20–24 Oct | Week 4 27–31 Oct |
| --- | --- | --- | --- | --- |
| Status | COMPLETE ✓ | IN PROGRESS | UPCOMING | UPCOMING |
| Theme | Discovery & Data Collection | Co-creation & Workshops | Strategy & Operating Model | Roadmap & Final Presentation |
| Pillars addressed | Foundation for all 6 pillars | ① Growth Strategy ② Product & UX | ③ Partner Strategy ④ Analytics & KPIs ⑤ Operating Model | ⑥ 3-Year Roadmap + Final Presentation |

WEEK 1  ·  6–10 Oct 2026  ·  COMPLETE

Week 1 is finalized.

All 6 discovery interviews conducted. 6 meeting summary documents produced. Student survey drafted and ready for distribution. Initial delivery plan shared with Akobir (Friday 9 Oct). ZEO Cup attendance confirmed for 12 Oct.

Interviews Completed

| Stakeholder | Role | Key Theme Surfaced |
| --- | --- | --- |
| Bobur | Founder & CEO | App stuck in demo state; no single agreed vision; resources to scale exist but clarity is the missing trigger |
| Sirojiddin | Head of Events / Youth Centre | 8 staff, 1000+ volunteers; events team has no shared app workflow; ZEO Cup live test on 12 Oct |
| Azam | Head of IT | Data loss incident; outsource team with no SLA or QA; no IP confirmation; delivery takes months |
| Alim | Head of Strategy & Partnerships | Ministry merger creates new govt access; university subscription model opportunity; org-wide misalignment |
| Akobir | Head of Media & App Lead | Events-media silo starves app; no data privacy notice; content drops to 5% when events are quiet |
| Aksana | UX Designer | App UI unchanged 1 year; designer has no access to files; images broken on Android for months |

Quick Wins — Actioned in Week 1 (Ziyo Forum side)

| Action | Owner | Deadline |
| --- | --- | --- |
| Add data privacy / consent notice to app registration — legal risk, must be fixed before any growth | Akobir + Azam | URGENT — this week |
| Confirm IP / source code ownership with tech partner in writing | Akobir / Azam | This week |
| Transfer ZEO app UI source files from Azam to Aksana (designer) | Azam + Aksana | This week |
| Fix Android image distortion — outsource team to resolve via direct coord with Azam | Azam + outsource team | This week |
| Share Ziyo Forum brand assets with SAP Team; SAP Team shares Canva template in return | Aksana + SAP Team | This week |
| Azam to share full tech architecture document with SAP Team | Azam | This week |
| Establish weekly events-media calendar sync (2-week forward view) | Akobir + Sirojiddin | This week |

WEEK 2  ·  13–17 Oct  ·  Pillars ① Growth Strategy  +  ② Product & UX

Week 2 shifts from listening to making. Two structured workshops anchor the week — Vision Workshop and SAP Masterclass — alongside working sessions with the tech and design leads. Outputs feed directly into the Growth Strategy and Product & UX deliverables.

① Growth Strategy — Attract, Activate & Retain Young Users

Goal: produce a written growth strategy that is grounded in the Uzbek student reality and actionable within Ziyo Forum's current resources.

User insight foundation: Student survey results (launched Week 1) analysed to understand motivation gaps, channel preferences, and barriers to app use

Activation mechanics: Map the current registration → first event → return visit funnel; identify the largest drop-off point; design one targeted fix

Retention design: Assess Zeocoin gamification — is the reward meaningful? Is the cadence right? Propose minimum changes to increase weekly app opens.

Channel strategy: Identify the 2 highest-ROI student acquisition channels (Telegram, university lectures, influencer, partner referral) given Ziyo Forum's team capacity

Ministry merger: Map how the newly merged Ministry of Education opens access to school-aged students (1 million who miss university). Propose one pilot.

University subscription model: Working session with Alim — draft value proposition and basic pricing concept for universities to promote via ZEO app

Growth Strategy Deliverable (end of Week 3)

A 10–15 page Word document: (1) User segmentation (who we are attracting), (2) Activation funnel analysis, (3) Retention mechanics, (4) Top 3 acquisition channels with effort/impact matrix, (5) Ministry merger opportunity, (6) University subscription concept. Presented in Week 4.

② Product & UX — Most Important Improvements

Goal: produce a prioritised list of product improvements grounded in user feedback, stakeholder interviews, and UX best practice — not a wish list, a ranked backlog.

Homepage redesign: Session with Aksana — review international reference apps (OneFit, one SAP suggestion); Aksana produces redesign sketches by end of week

Registration & onboarding flow: Map the current flow step-by-step; identify the most friction-heavy moment; propose a simpler version

Event discovery & RSVP: This is the single most-cited user complaint (Sirojiddin). Design a cleaner event card, registration confirmation, and QR check-in flow.

Content feed: Design a minimum content discipline — what appears on the home feed, in what order, how freshness is managed

Zeocoin UX: Review how coins are earned, displayed, and spent. Is it motivating? Is the balance visible? Propose one UX improvement.

Feature priority matrix: Score all proposed improvements on a 2x2 impact vs. effort grid. Top-right quadrant = immediate roadmap.

Product & UX Deliverable (end of Week 3)

A prioritised improvement list with wireframe sketches for the top 3 changes. Includes: feature priority matrix, annotated homepage concept, event registration redesign. Format: Word document + Aksana's design concepts (PDF).

Week 2 Sessions

| Session | Who | Duration | Output |
| --- | --- | --- | --- |
| SAP Masterclass | All Ziyo Forum staff (mandatory) | 1.5–2 hrs | Shared vocab for product development. Leave-behind: feature request template + spec template. |
| Vision Workshop | CEO + all 6 dept heads | 2 hrs | Single agreed written app vision statement signed by Bobur. Each dept head names one concrete change. |
| Growth Strategy Working Session | SAP Team + Alim + Akobir | 1.5 hrs | Draft acquisition channels, activation funnel map, retention mechanics review |
| Product & UX Working Session | SAP Team + Aksana + Azam | 1.5 hrs | Prioritised improvement list; Aksana starts homepage redesign sketches |
| Informal Team Gathering | All Ziyo Forum staff + SAP Team | Evening (2 hrs) | Ground-level insights; trust-building with non-manager staff. No agenda cards. |
| Cross-dept Content Sync (1st) | Events + Media + IT teams | 1 hr | Shared content calendar template; agreement on 2-week forward content visibility |

WEEK 3  ·  20–24 Oct  ·  Pillars ③ Partner Strategy  +  ④ Analytics & KPIs  +  ⑤ Operating Model

Week 3 is about building the infrastructure Ziyo Forum needs to grow sustainably: who are the right partners, how do you know if you're winning, and how does the team work day to day. All three pillars are co-designed with the Ziyo team — not handed down.

③ Partner Strategy — Universities, Companies, NGOs, Cultural Institutions

Goal: a scalable partnership model that Ziyo Forum can operate without SAP after the engagement — including a university subscription concept, employer pipeline, and NGO content partnerships.

| Partner Type | Value to Ziyo Forum | Proposed Model |
| --- | --- | --- |
| Universities | Content (courses, scholarships, events) + student reach | Subscription model: universities pay to feature their programmes and access the student database. Self-financing universities need student acquisition — ZEO is the channel. |
| Employers & Companies | Jobs/internships + Zeocoin sponsorship | Employer partner page: companies list student-friendly vacancies. Vacancy requirements feed the career-matching feature. Zeocoin marketplace — employers sponsor coin campaigns. |
| NGOs & Cultural Institutions | Events, grants, cultural programmes | Content partnership: NGOs supply event/grant listings in return for promotion to ZEO's student base. No payment — mutual audience reach. |
| International Organisations (UN, etc.) | Credibility, programmes, funding | Existing relationships (Bobur, Alim). Formalise as "featured partner" tier — special placement in app + co-branded content. Documents the partnership value in a repeatable pitch. |
| Ministry of Education (merged) | Government reach + school student access | Post-merger opportunity: propose one pilot project targeting last-year secondary students who miss university entry. Government visibility raises Ziyo Forum's legitimacy. |

Partner Strategy Deliverable (end of Week 3)

A scalable partner framework document: (1) Partner type definitions and value propositions, (2) University subscription model with sample pricing tiers, (3) Employer partnership template, (4) NGO content partnership agreement template, (5) Partnership pipeline prioritisation (who to approach first). Format: Word + one-page partner pitch template.

④ Analytics & KPIs — Metrics & Dashboards to Manage Growth

Goal: define the minimum set of metrics Ziyo Forum needs to know if the app is working — and a simple dashboard concept to track them. No big data system required. Start with what can be tracked today.

| Metric | What it measures | Current status | Target (12-month) |
| --- | --- | --- | --- |
| Monthly Active Users (MAU) | Are users returning? | Unknown — not tracked | TBD in workshop |
| New Registrations / week | Is acquisition working? | Unknown — not tracked | TBD in workshop |
| Event RSVP rate | Are users engaging with events? | Manual QR count only | TBD in workshop |
| Content posts / week | Is the content pipeline healthy? | ~5% of possible (content drought) | Min. 3 posts/week |
| Zeocoin earn/spend ratio | Is gamification motivating? | Not measured | TBD in workshop |
| Partner-sourced registrations | Is the partner strategy working? | Zero (no tracking) | TBD after model launch |
| App store rating | Are users satisfied? | Not monitored | Target: ≥ 4.0 |
| D7 / D30 retention | Do users come back after 7 / 30 days? | Not measured | TBD in workshop |

Analytics & KPIs Deliverable (end of Week 3)

A KPI framework document: (1) Agreed top 8 metrics with definitions, (2) Data source for each metric (app backend, app store, Trello, manual count), (3) Simple Excel dashboard template pre-filled with example data, (4) Review cadence: who looks at this, when, and what decisions it informs. Format: Word + Excel dashboard template.

⑤ Operating Model — Structured & Scalable Internal Processes

Goal: define how Ziyo Forum runs the app as an ongoing product — not how SAP would run it, but how a 5-person core team in Tashkent can run it the week after SAP leaves.

Core team: Product Owner (Akobir, interim → dedicated hire), Designer (Aksana), Tech Liaison (Azam), Content Coordinator (TBD from media), Outsource Dev Team

Weekly rhythm: Mon: content & events sync → Tue: design production → Wed: tech check-in with outsource → Thu: product owner review → Fri: 15-min retrospective + Trello update

Feature request process: Any staff member submits via Trello card template → Product Owner prioritises (P1/P2/P3) → Tech Liaison writes spec → Designer produces assets → Outsource builds → QA checklist → Product Owner sign-off → Release

Bug reporting: Any staff or user can report via Telegram bot (to be set up by Akobir). Tech Liaison triages. P1 bugs get same-day response from outsource under SLA.

Sprint cadence: 2-week sprints. First sprint starts: 27 October 2026 (Week 4). Backlog managed in Trello. Sprint demo every second Friday.

Tech partner SLA: P1 (blocking) — fix within 48 hrs. P2 (important) — fix within 1 week. P3 (polish) — next sprint. All work requires written spec before starting. QA checklist sign-off before any release.

CEO involvement: Monthly 30-min steering review with Bobur — top 3 metrics, top 3 decisions needed. Bobur is removed from day-to-day approvals.

Content pipeline minimum: At least 3 new items posted per week. Events team provides 2-week forward calendar to media team every Monday.

Operating Model Deliverable (end of Week 3)

A process playbook (Word, printable): (1) Core team org chart with roles and responsibilities, (2) Weekly rhythm calendar (Mon–Fri), (3) Feature request + bug fix process (7-step flowchart), (4) Sprint cadence overview, (5) SLA with outsource partner (ready-to-sign template), (6) Content pipeline minimum commitments.

WEEK 4  ·  27–31 Oct  ·  Pillar ⑥ 3-Year Roadmap  +  Final Presentation

Week 4 translates everything into a single coherent plan Ziyo Forum can act on for the next three years. The 3-Year Roadmap is presented to Bobur and the full team in a structured 2-hour session. All documents are transferred. The engagement closes.

⑥ 3-Year Roadmap — Priorities, Responsibilities & Milestones

Goal: a single document that every Ziyo Forum team member can look at and know what is happening, who is doing it, and when it should be done — for the next 3 years.

| Phase | Period | Theme | Key Milestones | Pillars |
| --- | --- | --- | --- | --- |
| NOW | Oct–Dec 2026 | Stabilise the foundation | • Data privacy notice live • IP confirmed with tech partner • SLA signed with outsource • Dedicated app team formed • Brand guidebook v1 complete • Content pipeline: 3 posts/week minimum | ⑤ Operating Model ② Product & UX |
| NEXT | Q1–Q2 2027 | Build the product that retains users | • Homepage redesigned and live • Event registration + QR flow overhauled • In-app analytics (MAU, retention) tracking • First university subscription signed • Zeocoin earn/spend redesign • Job/career matching MVP launched | ② Product & UX ① Growth ③ Partners ④ Analytics |
| LATER | H2 2027 & 2028 | Scale with data and partnerships | • 5+ university partners active • Employer partnership pipeline (10+ companies) • AI career path assistant (MVP) • Ministry of Education pilot programme • In-house dev team (2–3 people) hired • National scale ambition: outside Tashkent | ③ Partners ① Growth ⑥ Roadmap |

3-Year Roadmap Deliverable (Week 4)

A single-page visual roadmap (Word/PDF) + a detailed Word document: (1) NOW/NEXT/LATER framework with milestones, (2) Responsibility matrix — who owns each milestone, (3) Dependencies (what must happen before what), (4) Investment triggers (what decisions need to be made to unlock each phase). Presented to full team in the final session.

Final Presentation — 2 Hours  ·  Bobur + Full Ziyo Forum Team  ·  Thu or Fri Week 4

Format: PowerPoint (45–55 slides) + printed one-page summary for all attendees to keep

Structure: (1) What we found — top 10 findings, evidence, no surprises (30 min) → (2) Growth Strategy (15 min) → (3) Product & UX roadmap (15 min) → (4) Partner Strategy (15 min) → (5) Analytics & KPIs (10 min) → (6) Operating Model demo (10 min) → (7) 3-Year Roadmap (10 min) → (8) Open discussion (15 min)

Tone: Honest, direct, respectful. Framed as "here is what we recommend and why" — not a corporate report, a conversation with the team.

Leave-behind package: Printed summary card + USB or shared drive with all 13 deliverable documents

Full Deliverables Register — Mapped to Ziyo Forum's 6 Expectations

| Deliverable | Pillar | Format | Owner | Week |
| --- | --- | --- | --- | --- |
| 6 × Discovery Interview Summaries | — | Word (branded) | SAP Team | Week 1 ✓ |
| Student Survey | ① ④ | Google Form (Uzbek) | SAP Team + Sirojiddin | Week 1 ✓ |
| SAP Masterclass Deck + Session | ⑤ | PowerPoint + 1.5-hr session | SAP Team | Week 2 |
| Vision Workshop Pack + Output | — | Printed cards + Word output | SAP Team | Week 2 |
| Growth Strategy Document | ① | Word (10–15 pages) | SAP Team | Week 2–3 |
| Product & UX Improvement List + Sketches | ② | Word + design concepts PDF | SAP Team + Aksana | Week 2–3 |
| Partner Strategy Framework | ③ | Word + pitch template | SAP Team + Alim | Week 3 |
| Analytics & KPIs Framework | ④ | Word + Excel dashboard template | SAP Team | Week 3 |
| Operating Model & Process Playbook | ⑤ | Word (printable, with flowcharts) | SAP Team | Week 3 |
| Tech Partner SLA Template | ⑤ | Word (ready-to-sign) | SAP Team | Week 3 |
| ZEO App Brand Guidebook v1 | ② | PDF (colours, type, sizing specs) | Aksana + SAP Team | Week 3 |
| 3-Year Roadmap | ⑥ | Word + 1-page visual PDF | SAP Team | Week 4 |
| Final Presentation Deck | All 6 | PowerPoint (45–55 slides) | SAP Team | Week 4 |
| SOW Completion Report & Handover Notes | — | Word (2–3 pages) | SAP Team | Week 4 |

Mutual Expectations & Working Agreements

| SAP Team commits to Ziyo Forum: | Ziyo Forum commits to SAP Team: |
| --- | --- |
| • Deliver all 14 documents and sessions within the 4-week schedule • Ground every recommendation in what is achievable with Ziyo Forum's actual resources • Share findings honestly — including critical issues — in a constructive way • Transfer 100% of all work products; no IP retained by SAP • Attend ZEO Cup (12 Oct) to ground recommendations in lived experience • Produce in formats Ziyo Forum can edit, share, and build on independently | • Address the two urgent Week 1 quick wins (data privacy; IP) before end of Week 1 • Participate actively in workshops — not as observers but as co-designers • Give access to app systems, data, and non-manager staff as requested • Designate one Ziyo Forum POC for SAP Team coordination (suggest: Alim) • Implement agreed quick wins during the engagement — not defer everything post-SAP • Be transparent about constraints — budget, politics, team capacity |

Ziyo Forum  ·  SAP Social Sabbatical  ·  Tashkent, Uzbekistan  ·  October 2026        SAP Team  ·  Statement of Work  ·  Final v2.0  ·  8 Oct 2026